## Trial Protocol
⚙ FREE INDUSTRIAL TOOLKIT — METALLISER & r-PET TOOLS FROM THE PLANT FLOOR
VKS TECH ¦ https://vksTech.com ¦ Vivek Kumar (Privacy Papa) — M.Tech NIT Uttarakhand ¦ 9+ Years Flexible Packaging
📚 r-PET Compatibility · Trial Protocol · Hybrid Cost Optimisation ¦ Doc Ref: VKS/MET/RPET/02
🧪 r-PET LINE TRIAL PROTOCOL — STEP-BY-STEP
r-PET लाइन ट्रायल प्रोटोकॉल — चरण-दर-चरण
Trial Date: | [fill in] |  | Line: | [fill in] |  | Trial #: | [# ]
Step # | Phase चरण | Action / कार्रवाई | Target / लक्ष्य | Measure / मापें | Pass criteria / पास मानदंड | Owner / स्वामी | Status
1 | Pre-trial | Verify supplier CoA — IV, b* (yellowness), moisture, melting point, gel count | CoA matches spec | Compare to virgin PET CoA | IV ≥0.78 dL/g, b* ≤1.5, moisture <100 ppm | [QC]
2 | Pre-trial | Crystallise r-PET pellets if amorphous — 4 hours @ 130-160°C | Crystallinity ≥35% | DSC test or visual (white opaque) | ✅ White opaque pellets | [Process]
3 | Pre-trial | Dry r-PET pellets — 4-6 hours @ 160-170°C, dewpoint ≤ -40°C | Moisture <50 ppm | Karl Fischer titration | ✅ <50 ppm | [QC]
4 | Pre-trial | Set extruder zones for blended feedstock — anticipate +5-10°C melt temperature rise | Zone profile prepared | Trial recipe sheet | ✅ Recipe documented | [Process]
5 | Trial run | Start with 10% r-PET blend, ramp 5% increments every 30 min until target loading | Stable extrusion at each step | Visual + die head pressure | No surging, pressure ±5% | [Operator]
6 | Trial run | Sample film at each loading level — record speed, pressure, OD trend, gauge variation | Consistent gauge ±2% | Online thickness gauge | ✅ Within tolerance | [Operator]
7 | Trial run | Hold at target loading for ≥1 hour to stabilise crystallinity | Steady-state achieved | Speed + pressure stable 60 min | ✅ Stable run | [Operator]
8 | Sampling | Cut film samples at 0%, target loading, and target+10% loadings (3 samples × 1 m each) | 3 samples taken | Length measurement | ✅ 3 × 1m samples | [QC]
9 | Sampling | Hold trial roll separate — do NOT ship until QC clear | Roll quarantined | Roll tag + log | ✅ Quarantined | [QC]
10 | QC tests | Measure film yellowness (b* via colourimeter) | b* ≤3.0 standard / ≤2.0 premium | Hunter Lab or equivalent | ✅ Within target | [Lab]
11 | QC tests | Count gels / fish-eyes per 100 cm² — visual or automated | Gels ≤5/m² standard / ≤2/m² premium | Light box + magnifier | ✅ Within target | [Lab]
12 | QC tests | Measure tensile strength MD/TD vs virgin baseline | ≥95% of virgin | Tensile tester | ✅ ≥95% | [Lab]
13 | QC tests | Run pilot metallisation — record OD, adhesion, pinhole rate vs baseline | OD within ±5% of baseline | Densitometer + tape test | ✅ ±5% | [Met QC]
14 | Decision | Compare all QC results to pass criteria — go/no-go decision | All steps pass | Sign-off form | ✅ Cleared / ❌ Rejected | [Mgmt]
15 | Decision | If passed: lock recipe, update SOPs, brief operators. If failed: document failure mode + revert to virgin | Recipe locked OR root cause logged | SOP update or NCR report | ✅ Documented | [Process Lead]
📌 This protocol is a starting template. Modify pass criteria and steps based on your line, customer specs, and substrate. Quarantine all trial output until QC clears — never ship a trial roll without sign-off.
⚙ Built by a plant engineer for plant engineers — bilingual, free, and made for the floor.
🌐 Visit https://vksTech.com for more free formats, calculators, and training tools ¦ © VKS TECH — Vivek Kumar ¦ Share freely, do not resell